## Summery
		S/N Range			Date		Public		Sub-Assemblies
		First	Last	Length	From	To			Canvas	Interface	Motherboard

Engineering Sample		0001-e	0004-e	4	2020-02-17	2020-02-21	no		1	1	1, 2, 3
IGG18		0005-f	0014-f	10	2020-02-24	2020-03-15	yes		2	1	1, 2, 3
IGG18 + S.L.		0015-g	0025-g	11	2020-03-13	2020-03-20	yes		2	2	1, 2, 3
Pre		0026-g	0029-g	4					2	2	1, 2, 4
Pre		0040-h	0043-h	4			yes		3	2	1, 2, 4
Pre		0044-i							4

## Canvas
				Printer Settings					Routing					Mapmode
Revision	Known Issues	Recall Status			Design File	Resin	Scale X/Y	Scale Z	Profile	Attachment		Jig version	ID	Bit type	ID		Design File	Profile	Attachment

1		FALSE			canvas42	Wanhao Black	100.7	100.7	Wanhao Black (75um GRID)	2020-02-27		routing_template_1	1	MAKITA (D-47715)	1		mapmode_button_cap_7	Wanhao Black (75um GRID)	2020-02-27
2		FALSE			canvas42	Wanhao Black	100.7	100.7	Wanhao Black (75um GRID)	2020-02-27		routing_template_1	1	MAKITA (D-47715)	1		mapmode_button_cap_8	Wanhao Black (75um GRID)	2020-02-27
3	Too small outline	FALSE			canvas44	Prima Value Tough Black	0.3	0.3				routing_template_2	2	MAKITA (D-47715)	1
4		FALSE			canvas45	Prima Value Tough Black	0.3	0.3				routing_template_2	2	MAKITA (D-47715)	1

## Interface
				PCB Batch					FFC Batch					PCB SMT Assembly					FFC Soldering
Revision	Known Issues	Recall Status		Design File	Manufacturer	Order Date	Color		Design File	Manufacturer	Order Date	Color		Technology	Manufacturer	Solder Paste	Type		Technology	Manufacturer	Jig	Solder	Solder Type

1	FFC Break, POGO Cleaning	Soft		INTERFACE 2019/12	JLCPCB	2019/12	Green		FFC 2019/12	PCBWay	2019/12/11	Yellow		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	Black	Cynel	Sn99,3Cu0.7
2	Eary batch used old solder paste, boards are marked with visible ‘x’	No		INTERFACE 2019/12	JLCPCB	2020/2	Red		FFC 2020/2	PCBWay	2020/02/29	Yellow		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	White	Cynel	Sn99,3Cu0.7

## Motherboard
				Module Variant					PCB Batch					SMT Assembly					THT Assembly
Revision	Known Issues	Recall Status		Name	HWCFG				Design File	Manufacturer	Order Date	Order Code	Color		Technology	Manufacturer	Solder Paste	Type		Technology	Manufacturer	Solder	Type

1	QSPI Flash Footprint, Mapmode Footprint, USB Shiled Impedance location, FFC connector footprint	FALSE		PO16	0				G4_P16_B16	PCBWay	2019/7/5	W16488ASN115	Blue		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	Cynel	Sn99,3Cu0.7
2	QSPI Flash Footprint, Mapmode Footprint, USB Shiled Impedance location, FFC connector footprint	FALSE		BU16	128				G4_P16_B16	PCBWay	2019/7/5	W16488ASN115	Blue		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	Cynel	Sn99,3Cu0.7
3	Fader Footprint	FALSE		PBF4					PBF4	PCBWay	2019/9/6	W16488ASN126	Blue		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	Cynel	Sn99,3Cu0.7
4		FALSE		EN16					EN16	JLCPCB	2019/9/26	Y2-2619630A	Green		Manual	Intech Studio	Quick Chip	TS391SNL50		Manual	Intech Studio	Cynel	Sn99,3Cu0.7

## Shipping
Status		S/N:	Type:	Shipping	Currier	ID	Name

Shipped		0005-f	PBF4	2020/03/9	DHL	2	Gabriel Liberti
Shipped		0006-f	PBF4	2020/03/20	DHL	8	Sebastian Berweck
Shipped		0007-f	PBF4	2020/02/28	Local Pickup	1	Dániel Pásztor
Shipped		0008-f	PBF4	2020/03/9	DHL	3	Norman Danner
Shipped		0009-f	PBF4	2020/03/20	DHL	6	Hyogetsuka
Shipped		0010-f	BU16	2020/03/9	DHL	4	Eugene Radin
Shipped		0011-f	PBF4	2020/03/20	DHL	6	Hyogetsuka
Shipped		0012-f	PBF4	2020/03/9	DHL	5	Robin Thunnel
Shipped		0013-f	PO16	2020/03/9	DHL	2	Gabriel Liberti
Shipped		0014-f	PO16	2020/03/9	DHL	3	Norman Danner

Shipped		0015-g	PO16	2020/03/20	DHL	7	Jeff Griffiths
Shipped		0016-g	PO16	2020/03/20	DHL	8	Sebastian Berweck
Shipped		0017-g	BU16	2020/03/20	DHL	7	Jeff Griffiths
Shipped		0018-g	BU16	2020/03/20	DHL	6	Hyogetsuka
Shipped		0019-g	PBF4	2020/03/20	DHL	10	Sharon Li
Shipped		0020-g	PBF4	2020/03/20	DHL	9	Greg Meyer
Shipped		0021-g	PBF4	2020/03/20	DHL	7	Jeff Griffiths
Shipped		0022-g	BU16	2020/03/20	DHL	9	Greg Meyer
Shipped		0023-g	BU16	2020/03/20	DHL	8	Sebastian Berweck
Shipped		0024-g	PO16	2020/03/20	DHL	10	Sharon Li
Shipped		0025-g	PBF4	2020/03/20	DHL	10	Sharon Li

Shipped		0026-g	EN16	2020/04/3	DHL	14	Mike Caffrey
Shipped		0027-g	EN16	2020/04/3	DHL	15	David Borchardt
		0028-g	BU16
Shipped		0029-g	EN16	2020/04/3	DHL	16	Jan Sikl
		0030-g
		0031-g
		0032-g
		0033-g
		0034-g
		0035-g
		0036-g
		0037-g
		0038-g
		0039-g

Shipped		0040-h	PO16	2020/04/3	DHL	11	Michael Lang
Shipped		0041-h	BU16	2020/04/3	DHL	12	Paßen Heinz-Gerd
Shipped		0042-h	EN16	2020/04/3	DHL	12	Paßen Heinz-Gerd
Shipped		0043-h	PO16	2020/04/3	DHL	13	Simone Gardumi

Shipped		0044-i	PBF4	2020/04/21	DHL	17	Paxton Gregory
Shipped		0045-i	PBF4	2020/04/21	DHL	17	Paxton Gregory
Shipped		0046-i	PBF4	2020/04/21	DHL	18	Syu Ishihara
Shipped		0047-i	PBF4	2020/04/21	DHL	19	Pete Thurnbury
Shipped		0048-i	PBF4	2020/04/21	DHL	20	Magnus Stromberg
Shipped		0049-i	PO16	2020/04/21	DHL	19	Pete Thurnbury

Shipped		0050-i	PBF4	2020/04/27	DHL	23	Robert Watson
Shipped		0051-i	PBF4	2020/04/27	DHL	24	Brice Bailly
Shipped		0052-i	PBF4	2020/04/27	DHL	24	Brice Bailly
Shipped		0053-i	PBF4	2020/04/27	DHL	25	Teruhisa Konno
Shipped		0054-i	PBF4	2020/04/27	DHL	25	Teruhisa Konno
Shipped		0055-i	PBF4	2020/04/27	DHL	25	Teruhisa Konno
Shipped		0056-i	PBF4	2020/04/27	DHL	26	Priscilla Gomez
Shipped		0057-i	PBF4	2020/04/27	DHL	21	Robert Vann
Shipped		0058-i	EN16	2020/04/27	DHL	21	Robert Vann
Shipped		0059-i	EN16	2020/04/27	DHL	22	Carlos Poon
Shipped		0060-i	EN16	2020/04/27	DHL	26	Priscilla Gomez
Shipped		0061-i	PO16	2020/04/27	DHL	26	Priscilla Gomez

Shipped		0062-i	PBF4	2020/05/19	DHL	27	Miko Vachon
Shipped		0063-i	PBF4	2020/05/19	DHL	28	George Jennings
Shipped		0064-i	PBF4	2020/05/19	DHL	29	Jeppe Moeller Johansen
Shipped		0065-i	EN16	2020/05/19	DHL	29	Jeppe Moeller Johansen
Shipped		0066-i	EN16	2020/05/19	DHL	30	Felix Baarss

Shipped		0067-i	PBF4	2020/05/21	DHL	31	Nick Nielsen
Shipped		0068-i	PBF4	2020/05/21	DHL	32	Andrew Ngo
Shipped		0069-i	PBF4	2020/05/21	DHL	32	Andrew Ngo
Shipped		0070-i	PO16	2020/05/21	DHL	32	Andrew Ngo
Shipped		0071-i	PO16	2020/05/21	DHL	32	Andrew Ngo

Pending		0072-i	PBF4	2020/06/04	DHL	33	Robert Tunstall
Pending		0073-i	BU16	2020/06/04	DHL	34	Neel Shivdasani
Pending		0074-i	EN16	2020/06/04	DHL	34	Neel Shivdasani

56